GYANAM INSTITUTE BHAGALPUR YELLOW IDEA PLAN
UNBOX COMPUTING
PRITHA MUKHERJEE (D M MANAGER)
SHEKHAR SUMAN (GRAPHICS DESIGNER)

---
STORYLINE OF YELLOW IDEA PLAN
Junction point	Task	Assinged Persion	Remarks	Result	Status	Alternative
22/07	Audit report of website	Abhinash Nahak	Audit score(36 very poor)		Done
23/07	Hashtag and caption filteration	Pritha Mukherjee		Trending hash and organic traffic for Bhagalpur Bihar	Done
23/07	01 post design	Shekhar Suman	stroke		Done
24/07	02 post design	Shekhar Suman	stroke		Done
24/07	Hashtag filteration	Pritha Mukherjee	Educational , and result oriented	Reach by hashtag	Incomplete	Done of 25/07

---
25/07	03 post design	Shekhar Suman	stroke		Done
25/07	Hashtag and caption filteration for +2 school	Pritha Mukherjee		Trending hash and organic traffic for Bhagalpur Bihar	Done
26/07	04 post design	Shekhar Suman	stroke		Done
26/07	05 post design	Shekhar Suman	stroke		Done
27/07	Hashtag filteration	Pritha Mukherjee	Educational , and result oriented	Reach by hashtag	All report send to Satyam

---
28/07	03 04 05 post design	Shekhar Suman	stroke		Done
28/07	Goggle ad campaing R&D for bihar bhagalpur region	Pritha Mukherjee		All report and pricing send to satyam
29/07	Facebook ad camp desing R & D for bihar bhagalpur	Pritha Mukherjee
29/07	06 07 post design	Shekhar Suman
30/07	Instagram ad camp R & D	Pritha Mukherjee	Educational , and result oriented	Reach by hashtag	All report send to Satyam

---
30/07	08 09 10 post design	Shekhar Suman	stroke
31/07	All add campaing live by Fb, Ig, Google ads	Pritha Mukherjee
01/08	All report genration for client	Pritha Mukherjee
01/08	11 12 13 post design	Shekhar Suman
03/08	Platform review and post scheduling	Pritha Mukherjee

---
03/08	post design	Shekhar Suman	stroke
04/08	All add campaing by Fb, Ig, Google ads	Pritha Mukherjee	Monitoring and maintaing
05/08	Schedule post hashtag filteraion and captions	Pritha Mukherjee	For bhagalpur and it nearest district
06/08	14 15 16 post design	Shekhar Suman
07/08	All add campaing live by Fb , Ig , Google adds	Pritha Mukherjee

---
07/08	All report generation for lead	Shekhar Suman	Satyam Swet
08/08	All add campaing R & D. by Fb, Ig, Google ads	Pritha Mukherjee	Monitoring and maintaing
08/08	Schedule post hashtag filteraion and captions	Pritha Mukherjee	For bhagalpur and it nearest district
08/08	14 15 16 post design	Shekhar Suman
09/08	Platform review and post scheduling	Pritha Mukherjee	Independence day week special post scheduling

---
09/08
10/08
11/08
11/08
12/08